## Slide 1: CCNURCA project activities

## Slide 2: WP 1 Analysis of current situation in nursing education in EU and in the WB region
 |  | Activity | Status | OUTCOME
 | 1,1 | Analysis report of the current situation of the education in nursing in WB region | Finalized | Report finalized available on web – site
 | 1,2 | Comparative analysis EU/WB in education on bachelor level in nursing education | Finalized | Report finalized available on web – site
 | 1,3 | Road map defined | Finalized | Report finalized available on web – site

## Slide 3
2 | Design of new competence based curriculum | Stage | OUTCOME
2,1 | Investigation of Learning Outcomes and specific nursing skills in WB and EU partners | Finalized | Document created-learning outcomes matrix created
2,2 | Setting up the learning outcomes (educational objectives) for new curriculum in WB | Finalized | Document created
2,3 | New curriculum and ECTS | In progress | 
2,4 | Description of the practical nursing skills | Finalized | Document created
2,5 | Description of methodology for the assessment of the skills | Finalized | Training done

## Slide 4: WP 3 Training of teaching staff for running course units during pilot project
3 | Activity | Stage
3,1 | Education of staff in EU institutes and hospitals | Finalized

## Slide 5
4 | Capacity building of the nursing schools in the region | Status | Outcome
4,1 | Finding equipment for training in nursing skills | Finalized | Equipment

## Slide 6: Dissemination of project results
 | Activity | Stage
9,1 | Raised project awareness through development of web site | Finalized, continously
9,2 | Raised project awareness through development of newsletter | Finalized, continously
9,3 | Raised project awareness through info sessions for stake holders | Finalized, continously
9,4 | Raised project awareness through dissemination conferences | To be done