## Slide 1: Deadlines and responsibilities
Filip Dumez
Dejan Bokonjic
Srdjan Masic

## Slide 2: WP 1
1.1. Analysis of current nursing education in WB and EU (until 15.04.2014.)
Draft version: HUB-KAHO
Validation: All

## Slide 3: WP 1
1.2. Comparative analysis EU – WB (focus on Bologna)
Draft version: HUB-KAHO & UES
Validation: All

## Slide 4: WP 1
1.3. Road map- definition (meeting Mostar 6.04.-09.04.2014.???)
2 representatives from universities, two from ministries, one from EU and two from HUB-KAHO Practical proposal for further actions

## Slide 5: WP 2
2.1. Investigation of learning outcomes and nursing skills in EU and WB countries.
=> All send proposal for learning outcomes to UES and HUB-KAHO

## Slide 6: WP 2
2.2. Setting up learning outcomes for new curriculum (meeting in Zenica 04.06-07.06.2014.)
UES, UNZE and HUB-KAHO, Nursing association representative, 4 people for each university, 1 rep of ministry (core group for curriculum change)
Incl. Students & hospital rep.
Focus on competence matrix

## Slide 7: WP 2
2.3. New curriculum
Draft version (ALL) by end of june (1st version)
Validation by all WB partners by end of september

## Slide 8: WP 2
2.4. Description of practical nursing skills & pilot training (meeting in Belgium 12-15.10.2014.)
3 from WB universities
HUB – KAHO
SLOVAKIA

## Slide 9: WP 2
2.5. Description of assesments skills & pilot training (Groningen, 16-20.11.2014.)
3 from universities, 2 from HUB-KAHO, HANZE
+ all consortium members for consortium meeting

## Slide 10: WP 3
3. Training of teaching staff for running course units during pilot project
(early in the second year in PRESOV)
all consortium members
Incl. Hospital staff

## Slide 11: WP 4
4.1. Procurement of equipement ( ½ of total equipement => all WB partners against okt 2014 [preferably earlier])
4.2. Definition of new teaching materials (guideline for CBT in nursing, catalogue of knowledge and skills, handbooks for teaching and etc. => all WB partners)

## Slide 12: WP 5
5. Testing of the new curriculum through pilot project
  Implement assessment, ECTS description, adapt and integrate curriculum
Introduce Quality Assessment procedures in new programs
  Procedures on self assessment, external assessment, accreditation protocol
Ensure sustainability of project results
  Setting up a network, change legislation, organizational dimension, inter university agreements
Second & third year

## Slide 13: WP 8
8.1. Internal quality control (november 2014.)
(KU LEUVEN)
External quality control (december, 2014)
(TO BE DEFINED)

## Slide 14: WP 9
9.1. WEB site (continual activity) => All
Content management =>HUB-KAHO
9.2. Newsletter (every 2-3 month) => All Incl hard copy
9.3. Info session (e.g. brochure in diff. Languages) for stakeholders (each WB country, december 2014.)

## Slide 15: WP 10
10.1. Management of the project (continual activity); incl project reporting (HUB-KAHO & UES)
10.2 Organization of Consortium meetings
(HUB-KAHO & UES)