## Slide 1: Deadlines and responsibilities
TO DO LIST

## Slide 2: WP 2
Final version (ALL) by end of December
Matrix of competences, outcomes and goals by all WB partners by the 10th of December
Final version curriculum first draft end of december
Mentors:
Slovakia experts-Montenegro
Belgium experts-Bosnia
Holland experts-Albania

## Slide 3: WP 2
Matrix should contain-competences, learning outcomes and courses

## Slide 4: WP 3
Steering committee meeting,, 11th of December Montenegro
Working visits by mentors to partner universities-possibility

## Slide 5: WP 2
2.5. Description of assesments skills & pilot training (Groningen, 16-20.11.2014.)
3 from universities, 2 from Odiseey, HANZE
+ all consortium members for consortium meeting

## Slide 6: WP 3
3. Training of teaching staff for running course units during pilot project
(8/12 February in PRESOV)
all consortium members , Ministries
Incl. Hospital staff

## Slide 7: WP 4
4.1. Procurement of equipement ( ½ of total equipement => all WB partners starting the process deadline end of year
4.2. Definition of new teaching materials (guideline for CBT in nursing, catalogue of knowledge and skills, handbooks for teaching and etc. => all WB partners)-end of year

## Slide 8: WP 5
5. Testing of the new curriculum through pilot project
  Implement assessment, ECTS description, adapt and integrate curriculum
Introduce Quality Assessment procedures in new programs
  Procedures on self assessment, external assessment, accreditation protocol-evaluation of each meeting
Ensure sustainability of project results
  Setting up a network, change legislation, organizational dimension, inter university agreements
Second & third year

## Slide 9: WP 8
8.1. Internal quality control (november 2014.)
(KU LEUVEN)
External quality control (december, 2014)
(TO BE DEFINED)

## Slide 10: WP 9
9.1. WEB site (continual activity) => All
Content management =>Odiseey
9.2. Newsletter (every few months) => All Incl hard copy-second number by the end of February 2015
9.3. Info session (e.g. brochure in diff. Languages) for stakeholders (each WB country, by the middle of december 2014-in cooperation with Famy)

## Slide 11: WP 10
10.1. Management of the project (continual activity); incl project reporting
10.2 Organization of Consortium meetings
/Pressov meeting