## Slide 1: Strengthening Nursing in Bosnia and Herzegovina
First Steering Committee meeting
Sarajevo, 31.1.2013
Emira Dropic and Greet Van Malderen – project managers

## Slide 2: Project rationale (1)
Health systems across the world are faced with:
  increasing health demands, due to a.o. a rise in chronic diseases and demographic changes
  financial constraints
  Within this changing context, the large nursing workforce has invaluable potential to influence health outcomes in BiH population.
BUT:
  BiH health system and education of health care professionals focus on curative /secondary care, limiting the potential of the nursing workforce for current and future health needs, particularly those of vulnerable populations
  Additionally, significant gaps in nursing competencies and practice:
    negatively impact the effective operation of the country’s health system,
    weaken existing reform achievements (e.g. in family medicine)
    leave the country insufficiently prepared for the shifting health care needs of the population.

## Slide 3: Project rationale (2): Common vision 2020
  Methodology:
    Context analysis, stakeholder visioning workshops, stakeholder review of project proposal
    Participating stakeholders:
      Public sector (MoH, HIF, PHI, cantonal MoH, medical faculties, hospitals, MoE, MoCa, …)
      Private sector and Civil Society (AKAZ/ASKVA, doctor chambers, health professionals associations, patient representatives, …)
Output:
    Identification of a number of nursing related challenges that currently negatively affect the working of the nursing profession and therefore impede on overall health outcomes in BiH (see below)
    Formulation of a shared vision for nursing in BiH by 2020
    Insight for project methodology: participative approach and involvement of many stakeholders is necessary for genuine local ownership and commitment to the project of all parties to successfully address the issues of nursing in BiH.

## Slide 4: Project rationale (3)
Some challenges identified for nursing in BiH (context analysis and visioning sessions):
  Limited input from nursing into health policy-making
  Major gaps between nursing education and practice
  Lack of appropriate nursing standards, regulations and legislation
  Poorly defined roles and functions
  Nursing faculties lack nurses as teaching staff
  Nursing curricula lack practice education
  Limited continuing and post-graduate education
  …
THEREFORE:
  Ministers of Health in FBIH, RS and Brcko District agreed the need to improve the quality of nursing practice
  SDC agreed to sponsor project

## Slide 5: The Project Overall Goal
Health outcomes in Bosnia and Herzegovina are improved

## Slide 6: Project Purpose / Outcome
Increased quality and efficiency of nursing services, with a focus on the PHC level, and increased access to these services, in particular for vulnerable groups

## Slide 7: Intermediate Outcomes Project’s Components
Component 1: Nursing regulation, recognition, development and empowerment (organisation)
Component 2: Community nursing expansion and outreach development (services)
Component 3: Formal education of nurses (University level) (education)

## Slide 8: Component 1 - Outputs
  Regulation of nursing profession has improved
All cantons and both entities have a nurses’ chamber established and functional
Nurses’ associations are strengthened for representation of interests of their members
  Two resource centers for nurses are established

## Slide 9: Component 2 - Outputs
Community nursing services are designed based on international standards/ best practices and needs of vulnerable groups
Community nursing services are implemented and monitored in selected geographic areas and a strategy for scaling up has been developed

## Slide 10: Component 3 - Outputs
Competences of nurses educated at university level are defined in line with international standards, needs of population and reform requirements
Strategy for building local nurse faculty teaching capacities is developed

## Slide 11: Phase I of the Project
4 full calendar years, starting October 1st, 2012 until September, 30th 2016
geographical coverage: the project intervenes on a nation-wide basis, simultaneously in both entities of Bosnia-Herzegovina
focus on component 1 and 2 in phase 1
budget: 8'210'000 KM (5.1 million CHF)

## Slide 12: Project Donor and Consortium Partners
The Project is financed by SDC
Consortium Partners (3) take up the core responsibility for the project implementation:
  Fondacija fami
  University Hospital of Geneva (HUG)
  Institute of Nursing Science, University Basel (INS)
Further expertise: Swiss Red Cross, SBK/ASI, Basel Institute on Governance, WHO Maribor

## Slide 13
Component 1
Component Manager BiH
(Eldin Fisekovic)
Component Manager CH
(Nicolas Perone)
Project Manager CH
(Greet van Malderen)
Project Manager BiH
(Emira Dropic)
Project Leadership Team
Component Manager CH
(Lucien Portenier)
Component 2
Component Manager BiH
(Aldina Mahmutović)
Component Manager CH
(Alexander Bischoff)
Technical Advisor CH
(Thomas Vogel)
Technical Advisor
(Alexandra Papis)
Component 3
Component Manager FBiH
(Mediha Avdic)
Component Manager CH
(Rene Schwendimann)
Technical Advisor SL
(Tamara Lubi)
Project Administration
Finacial manager (Asim Rizvanovic)
Administrative Assistant (Zana Durakovic)
Transversal assistance
Project Assistant (Srdjan Djokic)
Project Assistant (Ana Sredic)
Director Fondacija fami
Project Associate (Senad Mavric)
Component Manager RS
(Duška Jović)

## Slide 14: Activities and outputs until present
Logistics:
  Offices and equipment, including project vehicles
Personnel:
  All project staff hired
  Job descriptions and ToRs of all project staff, component and project managers
  Project contact persons appointed in FMoH, MHSWRS and in MoCA
Project Planning finalization:
  detailed budget for year 1
  detailed activity plans for project management and component activities
  detailed planning of HR for year 1, based on the detailed activity plans
Project processes established/prepared:
  Monitoring system for HR
  Internal financial controlling
  Strategy for working groups made
  Communication mechanism for CMs (BH-Swiss) established
  Structure for intranet platform, including allocation of access rights, where relevant project documents will be shared between project team members
  By laws for Steering Committee drafted
  “Project corporate identity”
Project component activities:
  Data on nursing related regulation collected (C1)
  Research instruments (questionnaires etc.) drafted (C2)
  Data on formal education (competencies): data collection started (C3)

## Slide 15: General project activities planned (February)
Presentation of the project to main stakeholders (key nurses) – kick off
Finalization monitoring system (output and outcomes)
Education of key nurses on change management, moderation, team work, communication and conflict solving skills - Selection of participants for both events will be done in cooperation with MoHs, MoEs and government of Brcko district)
Subcontracting with University of Banja Luka for education of FM nurses in PAT with allocated money provided by SDC BiH, required by the MoHSWRS (BAM)
Subcontracting with an institution in FBiH for the project related to nurses with allocated money provided by SDC BiH, required by the FMoH (FPHI has made a project proposal (BAM)